## Sheet1
| school name | report date | location | recommended corrective action | category | notes | date of update | control number
561 | Lowell ES | 2013-01-10 | 1st Floor Hallway by 109A | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
562 | Lowell ES | 2013-01-10 | 1st Floor Men's Room (by Room 101) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster around window and bathroom entrance. | 2013-01-10 | 201255011
563 | Lowell ES | 2013-01-10 | 2nd Floor Hallway (by Room 206 above Water Fountain) | Scrape the loose sections of paint from the substrate. Painted surfaces should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint on the wall above the water fountain. | 2013-01-10 | 201255011
564 | Lowell ES | 2013-01-10 | 3rd Floor Hall Closet by 310 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
565 | Lowell ES | 2013-01-10 | 3rd Floor Hallway (by Room 306 above Water Fountain) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster on the wall. | 2013-01-10 | 201255011
566 | Lowell ES | 2013-01-10 | 3rd Floor Hallway (by Room 310) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster on ceiling. | 2013-01-10 | 201255011
567 | Lowell ES | 2013-01-10 | 3rd Floor Hallway (by Rooms 301A and 302) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed on window wall. | 2013-01-10 | 201255011
568 | Lowell ES | 2013-01-10 | 3rd Floor Hallway by 312 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
569 | Lowell ES | 2011-07-05 | Annex | Clean the particulate from the unit ventilator supply diffusers in the Annex. | Ventilation |  | 2011-07-05 | 2011735002
570 | Lowell ES | 2012-10-12 | Annex | Evaluate the bathroom exhaust fans and repair or issue a work order as needed. | Ventilation | The staff reported strong urine odors coming from the bathrooms in the annex. | 2013-01-10 | 2012255011
571 | Lowell ES | 2013-01-10 | Annex | Develop a proactive schedule to routinely clean Annex Unit Ventilators. | Ventilation | According to the Building Engineer, the Annex Unit Ventilators are not being cleaned on a routine basis. | 2013-01-10 | 201255011
572 | Lowell ES | 2013-01-10 | Annex 1st Floor Hall Elevator | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
573 | Lowell ES | 2013-01-10 | Annex 1st Floor Main Hall | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
574 | Lowell ES | 2013-01-10 | Annex 2nd Floor Main Hall | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
575 | Lowell ES | 2013-01-10 | Annex ABC Carpets | Assign a steam cleaning machine to this location and incorporate steam cleaning of the ABC carpets as part of the routine cleaning schedule. | Point Source | The staff indicated the 22 ABC carpets in the Annex are not being cleaned on a routine basis. During the IEQ meeting on 2/25/13, OEMS suggested that they will look into buying a steam cleaner for the school. | 2013-02-25 | 201255011
576 | Lowell ES | 2013-01-10 | Annex Room S-10 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
577 | Lowell ES | 2013-01-10 | Annex Room S-11 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
578 | Lowell ES | 2013-01-10 | Annex Room S-12 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. Several stained areas were painted with white paint. | 2013-01-10 | 201255011
579 | Lowell ES | 2013-01-10 | Annex Room S-13 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
580 | Lowell ES | 2013-01-10 | Annex Room S-14 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. Several stained areas were painted with white paint. | 2013-01-10 | 201255011
581 | Lowell ES | 2013-01-10 | Annex Room S-16 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. Several stained areas were painted with white paint. | 2013-01-10 | 201255011
582 | Lowell ES | 2013-01-10 | Annex Room S-17 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
583 | Lowell ES | 2013-01-10 | Annex Room S-18 | Evaluate the source of moisture and issue work order as needed for repair. | Mold/Moisture | Water damaged drywall to the right of the chalkboard. | 2013-01-10 | 201255011
584 | Lowell ES | 2013-01-10 | Annex Room S-18 | Replace water stained drywall to the right of the chalkboard. | Mold/Moisture | Water damaged drywall to the right of the chalkboard. | 2013-01-10 | 201255011
585 | Lowell ES | 2013-01-10 | Annex Room S-18 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
586 | Lowell ES | 2013-01-10 | Annex Room S-18 Bathroom | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
587 | Lowell ES | 2013-01-10 | Annex Room S-19 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
588 | Lowell ES | 2013-01-10 | Annex Room S-21 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
589 | Lowell ES | 2013-01-10 | Annex Room S-22 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
590 | Lowell ES | 2013-01-10 | Annex Room S-27 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
591 | Lowell ES | 2013-01-10 | Annex Room S-30 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
592 | Lowell ES | 2013-01-10 | Annex Room S-31 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
593 | Lowell ES | 2013-01-10 | Basement Boy's Bathroom | Scrape the loose sections of paint from the substrate. Painted surfaces should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint distributed on ceiling. | 2013-01-10 | 201255011
594 | Lowell ES | 2013-01-10 | Basement Boy's Room | Replace water stained fiberglass pipe insulation. | Mold/Moisture | Water stained fiberglass pipe insulation was observed above the toilets. | 2013-01-10 | 201255011
595 | Lowell ES | 2013-01-10 | Basement Cafeteria | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster by pipe penetration at entrance. | 2013-01-10 | 201255011
596 | Lowell ES | 2013-01-10 | Boiler Room | Replace water stained fiberglass pipe insulation. | Mold/Moisture | Water stained fiberglass pipe insulation was observed during the site evaluation distributed throughout the boiler room. | 2013-01-10 | 201255011
597 | Lowell ES | 2013-01-10 | Boiler Room | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed throughout the boiler room.. | 2013-01-10 | 201255011
598 | Lowell ES | 2012-10-12 | Building Wide | Continue aggressive IPM activity. | IPM | The PFT Building representative reported the biggest complaint in the building are the mouse droppings. | 2012-12-18 | 2012255011
599 | Lowell ES | 2013-04-26 | Building-Wide | Schedule an Environmental Action Team to address the issues and develop a plan of action. | Point Source | The PFT Building Representative Amy Kaufman indicated that several teachers have reported respiratory distress and feel the building may be contributing to their conditions. She indicated the biggest IEQ concerns in the building are related cleanliness and pest control. | 2013-04-26 | 2012255011
600 | Lowell ES | 2013-01-10 | Cleaning products | Consult Labor Relations relative to red germicidal Portion Pac causing allergic reaction and identify an alternative product as needed. OEMS contacted labor relations and no record of this report was found. | Point Source | The PFT Building representative reported she is allergic to the red germicidal Portion Pac cleaning solution. | 2013-02-25 | 201255011
601 | Lowell ES | 2013-01-10 | Exterior (Nedro Street) | Evaluate the placement of the security camera and relocate or install a camera that can function in low light conditions. | Safety | The staff reported the scaffolding over the door on Nedro Street is casting shadows making it difficult to identify visitors through the security camera. | 2013-01-10 | 201255011
602 | Lowell ES | 2013-01-10 | Exterior (Nedro Street) | Determine the status of the brick/pointing repairs for this location. | Safety | This location was identified as having loose mortar on the exterior of the building. As a precaution, scaffolding was erected over the Best door located on Nedro Street. | 2013-01-10 | 201255011
603 | Lowell ES | 2013-01-10 | Floor Cleaning Equipment | Repair or replace the floor cleaning machine. Cleaning equipment should be serviced and/or cleaned as needed. | Point Source | The building engineer reported the floor cleaning machine is not working properly. | 2013-01-10 | 201255011
604 | Lowell ES | 2013-01-10 | Kitchen | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
605 | Lowell ES | 2011-07-05 | Main Building and Annex | Develop a detailed cleaning plan of the building with input from the principal that includes high priority areas. The plan should also include; a procedure for cleaning the areas carpets, daily spot cleaning, deep cleaning schedule with steamer. A clutter cleaning schedule for the classrooms to keep surfaces open for cleaning. A procedure for addressing the rodent droppings as they are discovered including spills from lifting ceiling tiles. A procedure for the routine cleaning of the unit ventilators including filter change and interior and exterior cleaning. | Housekeeping | A housekeeping plan has been implemented by Facilities. The School Staff has reported significant improvement in overall cleanliness. | 2013-02-25 | 2011735002
606 | Lowell ES | 2013-01-10 | Main Building and Annex | Removed food waste from building and reline the trash cans with clean bags. | Housekeeping | The occupants reported when the food waste is removed from the trash cans the liners are not replaced. Additional food waste sticks to the bare trash can interior and attracts bugs. The B.E. indicated additional trashcan liners have been ordered and will be replaced on a regular basis. | 2013-01-10 | 201255011
607 | Lowell ES | 2011-07-05 | Main Building Classroom 108 Bathroom | Clean particulate from the exhaust ventilation grille. | Ventilation |  | 2012-12-18 | 2011735002
608 | Lowell ES | 2013-01-10 | Marble Stairs (Nedro Street) | Repair the chipped marble steps located at the Nedro Street entrance. | Safety | The staff reported several of the marble stairs on the Nedro Street side are chipped and presents a tripping hazard. | 2013-01-10 | 201255011
609 | Lowell ES | 2013-01-10 | Municipal Waste Dumpsters | Secure all entry points to Municipal Waste dumpsters located behind the school building on nights and weekends. | Point Source | The B.E. reported neighborhood residents are using the Municipal Waste dumpsters located behind the school building to dispose of their own waste. The vehicle entrances/exits are secured during the night and weekends, however pedestrian access points remain unsecure. | 2013-02-25 | 201255011
610 | Lowell ES | 2013-01-10 | Nedro Stairwell (Landing between 1st & 2nd Floor) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster to left of window. | 2013-01-10 | 201255011
611 | Lowell ES | 2013-01-10 | Nedro Stairwell (Landing between 2nd & 3rd Floor) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster. | 2013-01-10 | 201255011
612 | Lowell ES | 2013-01-10 | Nedro Stairwell (Landing between Basement & 1st Floor) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster. | 2013-01-10 | 201255011
613 | Lowell ES | 2013-01-10 | Room 100 (Nurse) | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
614 | Lowell ES | 2013-01-10 | Room 101 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
615 | Lowell ES | 2013-01-10 | Room 103 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster on left wall | 2013-01-10 | 201255011
616 | Lowell ES | 2013-01-10 | Room 104 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
617 | Lowell ES | 2013-01-10 | Room 104 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster. | 2013-01-10 | 201255011
618 | Lowell ES | 2013-04-26 | Room 105 | This location should be monitored during the summer months. If the floor tile begins to pop, the section of underlayment will need to be replaced. | Mold/Moisture | The teacher reported a leak occurred on the drinking water bubbler supply line in December 2012. Water leaked over an hour until the line was isolated. Water sprayed on the bulletin broad and covered the entire surface of the classroom floor. Following the leak, a section of the floor tile popped. When the floor tile was replaced at the end of January, she indicated the wooden underlayment was wet. She has been sick since February and was concerned if the wet underlayment is contributing to her condition. The underlayment where the section of floor tile that was replaced felt spongy, however, the floor tile was tight and no musty odors were observed. | 2013-04-26 | 2012255011
619 | Lowell ES | 2013-01-10 | Room 105 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster around windows. | 2013-01-10 | 201255011
620 | Lowell ES | 2013-01-10 | Room 107 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed throughout room. | 2013-01-10 | 201255011
621 | Lowell ES | 2013-01-10 | Room 108 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed throughout room. | 2013-01-10 | 201255011
622 | Lowell ES | 2013-01-10 | Room 108 (Bathroom) | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed throughout room. | 2013-01-10 | 201255011
623 | Lowell ES | 2013-01-10 | Room 109 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
624 | Lowell ES | 2013-01-10 | Room 109 A | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
625 | Lowell ES | 2013-01-10 | Room 110 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
626 | Lowell ES | 2013-01-10 | Room 111 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
627 | Lowell ES | 2013-01-10 | Room 201A | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
628 | Lowell ES | 2013-01-10 | Room 202 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
629 | Lowell ES | 2013-01-10 | Room 203 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
630 | Lowell ES | 2013-01-10 | Room 203 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster on ceiling and around door. | 2013-01-10 | 201255011
631 | Lowell ES | 2013-01-10 | Room 204 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
632 | Lowell ES | 2013-01-10 | Room 205 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
633 | Lowell ES | 2013-01-10 | Room 205 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster behind radiator. | 2013-01-10 | 201255011
634 | Lowell ES | 2013-01-10 | Room 206 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
635 | Lowell ES | 2013-01-10 | Room 206 | Scrape the loose sections of paint from the substrate. Painted surfaces should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint. | 2013-01-10 | 201255011
636 | Lowell ES | 2013-01-10 | Room 207 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
637 | Lowell ES | 2013-01-10 | Room 208 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
638 | Lowell ES | 2013-01-10 | Room 210 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
639 | Lowell ES | 2013-01-10 | Room 211 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
640 | Lowell ES | 2013-01-10 | Room 212 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
641 | Lowell ES | 2013-01-10 | Room 301A | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
642 | Lowell ES | 2013-01-10 | Room 301B | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
643 | Lowell ES | 2013-01-10 | Room 302 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed throughout room and behind radiators. | 2013-01-10 | 201255011
644 | Lowell ES | 2013-01-10 | Room 303 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
645 | Lowell ES | 2013-01-10 | Room 304 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
646 | Lowell ES | 2013-01-10 | Room 307 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
647 | Lowell ES | 2013-01-10 | Room 308 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
648 | Lowell ES | 2013-01-10 | Room 309 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster distributed around room and above room entrance. | 2013-01-10 | 201255011
649 | Lowell ES | 2013-01-10 | Room 309 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
650 | Lowell ES | 2013-01-10 | Room 311 | Replace water stained ceiling tiles. | Mold/Moisture | During the evaluation, water stained ceiling tiles were observed. | 2013-01-10 | 201255011
651 | Lowell ES | 2013-01-10 | Room 311 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster surrounding the windows. | 2013-01-10 | 201255011
652 | Lowell ES | 2013-01-10 | Room 312 | Scrape the loose sections of paint from the substrate. Painted surfaces should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint distributed on wall and ceiling. | 2013-01-10 | 201255011
653 | Lowell ES | 2013-01-10 | Room B-9 | Scrape the loose sections of plaster from the substrate. Painted surfaces associated with the damaged plaster should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint and plaster by teacher's desk and surrounding windows. | 2013-01-10 | 201255011
654 | Lowell ES | 2013-01-10 | Room B-9 Instrument Storage Closet | Replace fiberglass pipe insulation exhibiting visible mold growth with new fiberglass pipe insulation. A mold DDC was issued on 1/8/2013. | Mold/Moisture | Visible mold growth was observed on fiberglass pipe insulation located in the instrument storage closet. | 2013-02-25 | 201255011
655 | Lowell ES | 2013-01-10 | Stairwell by 211 | Scrape the loose sections of paint from the substrate. Painted surfaces should be assumed to contain lead based paint and treated accordingly. | Point Source | Water damaged paint on concrete block wall by double door. | 2013-01-10 | 201255011